**AVATAR Action Plans for Spring 2014**

**Implemented by: Heart of Texas P-20 Council and Education Service Center Region 12**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | **Action** | **Who**  | **What**  | **When**  | **Where**  | **How**  | **Expected Outcome** |
| 1. | Host Course Team Training | Fred Hills, HOT P-20 Building Capacity Chair (MCC) | Reserve Space at MCC | January 2014 | McLennan Community College | Teacher Stipend & Sub reimbursement | Critical Conversations on CRAfT Lessons |
| 2. | Facilitate Meeting | Chris Holecek, ESC Region 12 | Record findings | January 2014 | McLennan Community College | Facilitation Process | Record notes generated from critical conversations |
| 3. | Create online posting and collaboration site for course team members | Lisa Monthie,ESC 12 Consultant | Secure wikispace | Prior to January meeting 2014 | McLennan Community College | Wikispace | Participants will collaborate on artifacts from CRAfT lessons |
| 4. | Host Course Team Training | Fred Hills, HOT P-20 Building Capacity Chair (MCC) | Reserve Space at MCC for February | Prior to February 2014 meeting | McLennan Community College | Teacher Stipend & Sub Reimbursement | Critical Conversations on CRAfT lessons |
| 5. | Facilitate Meetings | Chris Holecek, ESC Region 12 | Record findings  | February 2014 Meeting | McLennan Community College | Facilitation Process | Record notes generated from critical conversations |
| 6. | College Prep proposal from MCC to satisfy HB5 requirement | Dr. Fred Hills, Londa Carriveau, and additional staff from MCC | Held separate meetings on Math, ELAR and Endorsements | March 2014 and ongoing conversations | McLennan Community College | All school districts invited to attend  | Overview of College Prep course development with input from AVATAR course team |
| 7. | Course team members take TSI assessment for informational purposes | AVATAR course team members | Compare TSI assessment to CRAfT lessons and College Prep lessons | May 9, 2014 and ongoing conversations | McLennan Community College | Teacher Stipend & Sub Reimbursement | Compare experiences taking the TSI assessment. Identify student experiences for college readiness |
| 8. | Celebrations | Sheryl Kattner-Allen, HOT P-20 Program Chair (TSTC) | Host a celebration event for P-20 Council and Team Members | May 9, 2013 | McLennan Community College | Invitations to team members, P-20 executive steering committee members and district superintendents and principals | Buy in from member organizations to continue project for school year 2014-2015. |